## Sheet1
Date | Resource | Module | Planned hrs | Exp. (%) of Completion | Actual hrs | Actual %of Completed | Status | Comments
2019-10-24 | chandrasekhar | Colive_Webservice_QA -> Property -> Send Common Notifications | 2 | 100 |  |  | In Progress | to send notifications to all app download users
2019-10-24 | chandrasekhar | Cbox QA ->Marketing ->Communication -> Push Notification -> Nodification | 2 | 100 |  |  | In Progress | to send notifications to all app download users
2019-10-24 | chandrasekhar | Firebase Document | 4 | 50 |  |  | In Progress | checking the possibilities to send the Notifications
Date | Module | Task/Activity | Expt date of delivery | Planned hr | Plan % completion | Comments
2019-10-24 | Colive_Webservice_QA -> Property | SendCommon Notification | 2019-10-24 | 2 | 100% | push notification checking functionality
2019-10-24 | Cbox QA - Marketing -Communication - Push Notification | Notification | 2019-10-24 | 1.5 | 100%
2019-10-24 | Firebase Document | Including Cluster name and city in property of month listing | 2019-10-24 | 4 | 100% | checked firebase document for push notification
2019-10-24 | Cbox QA - Property Rating | sorting and check box checked issues | 2019-10-24 | 0.5 | 100% | fixed
Date | Module | Task/Activity | Expt date of delivery | Planned hr | Plan % completion | Actual Hrs | Actual% completion | Status | Comments
2019-10-24 | Website-SearchResult | Including Cluster name and city in Property Listing | 2019-10-24 | 0.25 | 100% | 5 | 100% | WIP
2019-10-24 | Website-Factsheet | Including Cluster name and city in Address Details | 2019-10-24 | 0.25 | 100% | 0.25 | 100% | WIP
2019-10-24 | Website-Home Page | Including Cluster name and city in property of month listing | 2019-10-24 | 0.25 | 100% | 0.25 | 100% | WIP
2019-10-24 | Cbox-Owner Payment | Provision to reinitiate the failed transaction aspx changes & SpChanges | 2019-10-24 | 4 | 100% | 5 | 100% | WIP
2019-10-24 | Cbox-Customer Refund | Provision to reinitiate the failed transaction aspx changes & SpChanges | 2019-10-24 | 4 | 100% | 3 | 90% | WIP | Only Unit testing Pending ,Delay due to change of requirment
Date | Module | Task/Activity | Expt date of delivery | Planned hr | Plan % completion | Actual Hrs | Actual% completion | Status | Comments
2019-10-30 | Website-QA | More Filter functionality with UI Design | 30-10-2019 | 4hr | 100% | 5hr | 50% | WIP
2019-10-30 | Website-QA | Onclick functionality for singleroom, sharedRoom, CoupleRoom | 30-10-2019 | 4hr | 100% | 3hr | 70% | WIP

## Sheet2
Date | Resource | Module | Planned hrs | Exp. (%) of Completion | Actual hrs | Actual %of Completed | Status
2019-10-23 | Manojkumar | Coordination with Team and development for the day | 1 | 100%
2019-10-23 | Manojkumar | Customer & Owner Payout Meeting with Finance, Ops, Tech & product | 2 | 100%
2019-10-23 | Manojkumar | Payment Gateway Integration (PayU and CCA): | 6 | 100%
Working for CCAvenue payment pages and need to deploy in QA and test response (Request and response pages)
2019-10-23 | Manojkumar
2019-10-23 | Manojkumar
2019-10-23 | Manojkumar