## Sheet1
S.NO	Department	Employee Name	E- Mail Id	Contact Number	Verticles	Module	Goal set for November,2019	Goal Achieved for the month of November,2019	Goal set for December,2019
1	Tech	Uday	Sivakumar@colive.com	9894636002	Mobile	1.ICICI Integration(Live)-	1.Customer Due/Reservation/Check In Payment Integration
2	Tech	Uday	Sivakumar@colive.com	9894636003	Mobile	1.ICICI Integration(Live)-	2.Payment gateway Aggregator Page
3	Tech	Uday			Mobile	2.Property Average Rating(Live)	2.Property Average Rating(Live)
4	Tech	Uday			Mobile	3.Search and Property Tagging(Live)	1.Search Logic changes
5	Tech	Uday			Mobile	3.Search and Property Tagging(Live)	2.Gold & Platinum tags
6	Tech	Uday			Mobile	3.Search and Property Tagging(Live)	3.Almost Full & FastFilling Tags
7	Tech	Uday			Mobile	4.Notice Period and cancelation by customer(UAT)	4.Notice Period and cancelation by customer(UAT)
8	Tech	Ankit			Mobile	Attendance	2.Sign/Sign Out
9	Tech	Ankit			Mobile	Attendance	3.Attendance History
10	Tech	Ankit			Mobile	Attendance	4.(GEO Location Tracking)
11	Tech	Ankit			Mobile	1.BD Inbox	2.Location Capture
12	Tech	Ankit			Mobile	1.BD Inbox	3.Agent & Owner Mapping
13	Tech	Ankit			Mobile	1.BD Inbox	4.Area Details
14	Tech	Manoj			Web	1.ICICI Integration(Live)-	1.Customer Due/Reservation/Check-In Payment Integration
15	Tech	Manoj			Web	1.ICICI Integration(Live)-	2.Payment gateway Aggregator Page
16	Tech	Manoj			Web	1.ICICI Integration(Live)-	3.Payment Reconciliation
17	Tech	Manoj			Web	Signzy Integration(WIP)	Test Application on Signzy API
18	Tech	Manoj			Web	Static Page Routing and Backend Integration
19	Tech	MAnoj			Web	Zoho	GCLID capture in all landing pages and ZOHO
36	Tech	Manoj			Web	1.Website Support and Maintenance	6)Corporate Page - Lead Capture and Design/Content Change
20	Tech	Ranjith			Web	3.Search and Property Tagging(Live)	1.Search Logic changes
21	Tech	Ranjith			Web	3.Search and Property Tagging(Live)	2.Gold & Platinum tags
22	Tech	Ranjith			Web	3.Search and Property Tagging(Live)	3.Almost Full & FastFilling Tags
23	Tech	Ashwin			Web	Static Page front End Integration	City/Cluster/Location URL Routing & SEO Tagging
24	Tech	Ashwin			Web	Carrier Page	1.Content , images & UI changes
25	Tech	Ashwin			Web	Reservation Filter	1.Reservation Filter on website (Live) & App (WIP)
26	Tech	Shipha			Web	Notice Period	1.Cancel raised notice period & clear OS dues (UAT)
27	Tech	Shipha			Web	Notice Period	1.Banner redirection to the respective page based in city location
28	Tech	Rambalaji			Web	Studiohype.in	1.Design completed
29	Tech	Rambalaji			Web	1.Website Support and Maintenance	1)Handbook Image Updation
30	Tech	Rambalaji			Web	1.Website Support and Maintenance	2)Landing page content change
31	Tech	Rambalaji			Web	1.Website Support and Maintenance	1)Change colour of submit button in landing page(and highlight it) at present same colour as of background colour.
32	Tech	Rambalaji			Web	1.Website Support and Maintenance	2)Remove Zoho chat & GTM Code from landing page.
33	Tech	Rambalaji			Web	1.Website Support and Maintenance	3)Website Responsive Check for Different Mobile View (corporate, cowork247, our partner ,community, about us, news, contact us & top banner layout changed for corporate, cowork247.
34	Tech	Rambalaji			Web	1.Website Support and Maintenance	4)SEO Improvements
35	Tech	Rambalaji			Web	1.Website Support and Maintenance	5)Landing Page Responsive Design
37	Tech	Ganesh			Cbox	1.Attendance flow and geo tagging.	1.Live user Tracking
39	Tech	Ganesh			Cbox	1.Attendance flow and geo tagging.	3.Notification to mark attendance
47	Tech	Ganesh			Cbox	Reports	2.Availability screen changes
48	Tech	Ganesh			Cbox	Reports	3.Rate Card Report
50	Tech	Ganesh			Cbox	Collection	Outstanding Revenue Tracking and waive off Flow(LIVE)
40	Tech	Haritha			Cbox	1.Shona Calling	1.Rent Outstanding reminder
41	Tech	Haritha			Cbox	1.Shona Calling	2.Checked in not moved in reminder
42	Tech	Haritha			Cbox	1.Shona Calling	3.Reserved not checked in
43	Tech	Haritha			Cbox	1.Shona Calling	4.KYC
44	Tech	Haritha			Cbox	1.Shona Calling	5.Notice Period Updated.
52	Tech	Haritha			Cbox	ServiceTicket	Service ticket Improvements(LIVE)
57	Tech	Haritha			Cbox	Shona calling	Scheduler for Shona Calling(UAT)
45	Tech	Ranjith			Cbox	1.Website search logic changes	1.Platinum/Gold Tagging
46	Tech	Ranjith			Cbox	Reports	1.Colour Change for notice period
49	Tech	Ranjith			Cbox	Invoice	Invoice Change and payment Deduction order changes(LIVE)
51	Tech	Vijay			Cbox	PG Reconcillation	Delayed Payment Reconciliation for PayU And ICICI(LIVE)
53	Tech	Vijay			Cbox	Coupon	Fixed Amount Checkin Coupon (LIVE)
54	Tech	Chandrasekar			Cbox	BD inbox(LIVE)	BD inbox Search/view
55	Tech	Chandrasekar			Cbox	BD inbox(LIVE)	BD inbox Edit
56	Tech	Chandrasekar			Cbox	BD inbox(LIVE)	BDInbox APP API
58	Tech	Manikandan			Cbox	Collection	Oct Arrear Exclusion Flow(LIVE)
59	Tech	Manikandan			Cbox	ServiceTicket	Priority Tat Mapping (LIVE)
38	Tech	Manikandan			Cbox	1.Attendance flow and geo tagging.	2.Department wise hour configuration
60	Tech	Vickram			Angular Migration	Home Page
61	Tech	Vickram			Angular Migration	Search
62	Tech	Vickram			Angular Migration	Property Page