## Sheet1
S.NO	Department	Employee Name	E- Mail Id	Contact Number	Verticles	Module	Goal set for November,2019	Goal Achieved for the month of November,2019	Goal set for December,2019
1	Tech	Vikram	pabbojuvikram@gmail.com	9902928618	Angular Migration(Website)	Home Page	Hompage all UI design with API / Functionalities Include Header and Footer. / (Live)	Code Review / Code analysis / Website-QA Deployed / Description:Header Component navbar UI design and Functionality / with API. Routing to Different pages in Header Component. / UI design for About uspage ,Community Page, SingleRoom ,SharedRoom / ,Couple Room With Ngu-carosel UI with Functionalites. / See what our Members Say… new Carosel Cards. Our Features tabs / UI design. And Footer Component UI design.
2	Tech	vikram	pabbojuvikram@gmail.com	9902928618	Angular Migration(Website)	Search	Search Logic UI design with API key based on / Searching Different Properties (Live)	Code Review / Code analysis / Website-QA Deployed / Description:Search UI design with Functionality based on / Google API showing different property list
3	Tech	vikram	pabbojuvikram@gmail.com	9902928618	Angular Migration(Website)	Property Listing Page	Propertylisting Page In Property and Similar / Properties (Live)	Code Review / Code analysis / Website-QA Deployed / Description: Propertylisting page connecting with API get all details / Of Property cards and Similar properties
4	Tech	Vikram	pabbojuvikram@gmail.com	9902928618	Angular Migration(Website)	Detailed Propertylisting / Page	Each property card configuring with / Different API (Live)	Code Review / Code analysis / Website-QA Deployed / Description:here we are Each property connecting to multiple API’S / and Map inside showing distance between property and Bus stop, / airport and Railway station...etc. Polygan UI design with API Functionality
5	Tech	Vikram	pabbojuvikram@gmail.com	9902928618	Angular Migration(Website)	Filter and Map Functionality	Based On Property showing in Map filtering / Property	Code analysis / Code Review / Website-QA Deployed / Description:Filter more Based on Range of property rate we are filter / Properties and as well as we need to show the map.